## Sprint backlog
Wayfare: sprint backlog
Source: Trello board https://trello.com/b/MFhbwJxe/wayfare, read on 15 Oct 2026. One row per card, in board order. Status is Done when the due date is ticked complete on the card. Days = Due - Start + 1.
WBS | Sprint | Card | Labels | Members | Start | Due | Days | Status | Trello card
1.1 | Sprint 1 | Set up GitHub and add project members |  | Kerollos | 2026-09-23 | 2026-09-24 |  | Done | https://trello.com/c/pbxrXGua
1.2 | Sprint 1 | Project requirements |  | Whole team | 2026-09-24 | 2026-09-27 |  | Done | https://trello.com/c/z2inEAyY
1.3 | Sprint 1 | Choose the web stack |  | Whole team | 2026-09-27 | 2026-09-27 |  | Done | https://trello.com/c/poem249a
1.4 | Sprint 1 | Determine the project structure |  | Whole team | 2026-09-27 | 2026-09-27 |  | Done | https://trello.com/c/Y49jBrQV
1.5 | Sprint 1 | Front-end wireframe | Integrating with Frontend | Abdelrahman | 2026-09-27 | 2026-09-30 |  | Done | https://trello.com/c/1aZ2m2yk
1.6 | Sprint 1 | Front-end review and notes | Integrating with Frontend, Testing | Mina, Kerollos | 2026-09-30 | 2026-10-03 |  | Done | https://trello.com/c/E47IsomR
2.1 | Sprint 2 | Business flow and requirements |  | Whole team | 2026-10-03 | 2026-10-03 |  | Done | https://trello.com/c/IZKHleJT
2.2 | Sprint 2 | Entities and their attributes |  | Kerollos | 2026-10-03 | 2026-10-04 |  | Done | https://trello.com/c/OfLrs972
2.3 | Sprint 2 | Install the required NuGet packages |  | Mina, Kerollos | 2026-10-04 | 2026-10-04 |  | Done | https://trello.com/c/LiJgQ3Pm
2.4 | Sprint 2 | ERD and its documentation | Database | Mina | 2026-10-05 | 2026-10-07 |  | Done | https://trello.com/c/qKKuvXoH
2.5 | Sprint 2 | Back-end models and enums | Feature | Mina | 2026-10-07 | 2026-10-09 |  | Done | https://trello.com/c/oxyW7ctG
2.6 | Sprint 2 | List all API endpoints |  | Mina | 2026-10-09 | 2026-10-10 |  | Done | https://trello.com/c/A54TWQNu
2.7 | Sprint 2 | DbContext and database | Database, Milestone | Kerollos | 2026-10-09 | 2026-10-11 |  | Done | https://trello.com/c/EZ9lnIYX
2.8 | Sprint 2 | Bug fixing and edits | Testing | Whole team | 2026-10-03 | 2026-10-13 |  | Done | https://trello.com/c/h3qVbUWz
2.9 | Sprint 2 | Back-end data configurations | Database | Kerollos | 2026-10-11 | 2026-10-13 |  | Done | https://trello.com/c/K72zYdgA
3.1 | Sprint 3 | Login controller | Feature |  | 2026-10-13 | 2026-10-15 |  | To do | https://trello.com/c/6yknThto
3.2 | Sprint 3 | Register controller | Feature |  | 2026-10-13 | 2026-10-15 |  | To do | https://trello.com/c/IIN7A8qu
3.3 | Sprint 3 | Register DTO and its mapper | Feature |  | 2026-10-13 | 2026-10-15 |  | To do | https://trello.com/c/vEIV10KO
3.4 | Sprint 3 | Login DTO and its mapper | Feature |  | 2026-10-13 | 2026-10-15 |  | To do | https://trello.com/c/T825V92l
3.5 | Sprint 3 | Fix enum typos and add Rental fields | Database |  | 2026-10-15 | 2026-10-16 |  | To do | https://trello.com/c/Vn43DkQX
3.6 | Sprint 3 | Program.cs setup | Feature |  | 2026-10-15 | 2026-10-16 |  | To do | https://trello.com/c/CYEYdoCJ
3.7 | Sprint 3 | ListCar controller | Feature |  | 2026-10-15 | 2026-10-17 |  | To do | https://trello.com/c/QP40LNBB
3.8 | Sprint 3 | ListCar DTO and its mapper | Feature |  | 2026-10-15 | 2026-10-17 |  | To do | https://trello.com/c/jQtCx9ab
3.9 | Sprint 3 | RentalRules service | Feature |  | 2026-10-16 | 2026-10-17 |  | To do | https://trello.com/c/TExOruDr
3.10 | Sprint 3 | Seed roles, admin account and sample cars | Database |  | 2026-10-16 | 2026-10-17 |  | To do | https://trello.com/c/0pL339MB
3.11 | Sprint 3 | Image storage service | Feature |  | 2026-10-16 | 2026-10-17 |  | To do | https://trello.com/c/WPmSJB3H
3.12 | Sprint 3 | Branches endpoint | Feature |  | 2026-10-17 | 2026-10-17 |  | To do | https://trello.com/c/SdEdmdWh
3.13 | Sprint 3 | Authentication and authorization with Identity + JWT | Milestone, Feature, Authentication |  | 2026-10-17 | 2026-10-19 |  | To do | https://trello.com/c/YnKxkEPO
3.14 | Sprint 3 | ChangePassword endpoint | Authentication, Feature |  | 2026-10-19 | 2026-10-20 |  | To do | https://trello.com/c/ZNfG4BXB
3.15 | Sprint 3 | Testing with the front end | Integrating with Frontend |  | 2026-10-13 | 2026-10-21 |  | To do | https://trello.com/c/HPVKFVOq
3.16 | Sprint 3 | Bug fixing and edits | Testing |  | 2026-10-13 | 2026-10-22 |  | To do | https://trello.com/c/FDMITjOf
3.17 | Sprint 3 | .http file for every endpoint | Testing |  | 2026-10-15 | 2026-10-22 |  | To do | https://trello.com/c/ewzo1CUj
4.1 | Sprint 4 | ListMyRentals controller | Feature |  | 2026-10-23 | 2026-10-25 |  | To do | https://trello.com/c/sYUsWQ6o
4.2 | Sprint 4 | ListRentals DTO and its mapper | Feature |  | 2026-10-23 | 2026-10-25 |  | To do | https://trello.com/c/kU0U0Ms6
4.3 | Sprint 4 | CarDetails endpoint (customer) | Feature |  | 2026-10-23 | 2026-10-25 |  | To do | https://trello.com/c/zesf9oYV
4.4 | Sprint 4 | RentalRequest controller | Feature |  | 2026-10-25 | 2026-10-27 |  | To do | https://trello.com/c/gEnSeHBT
4.5 | Sprint 4 | RentalRequest DTO and its mapper | Feature |  | 2026-10-25 | 2026-10-27 |  | To do | https://trello.com/c/OJIHKKam
4.6 | Sprint 4 | CancelRental controller | Feature |  | 2026-10-27 | 2026-10-29 |  | To do | https://trello.com/c/SLynyBL4
4.7 | Sprint 4 | UserProfileDto and its mapper | Feature |  | 2026-10-29 | 2026-10-31 |  | To do | https://trello.com/c/8O9KrEim
4.8 | Sprint 4 | GetUserProfile controller | Feature |  | 2026-10-29 | 2026-10-31 |  | To do | https://trello.com/c/WtUZaQGB
4.9 | Sprint 4 | RefuseRental controller | Feature |  | 2026-10-29 | 2026-10-31 |  | To do | https://trello.com/c/7PbQrPyP
4.10 | Sprint 4 | Testing with the front end | Integrating with Frontend |  | 2026-10-23 | 2026-11-02 |  | To do | https://trello.com/c/cvPQAwAl
4.11 | Sprint 4 | Bug fixing and edits | Testing |  | 2026-10-23 | 2026-11-02 |  | To do | https://trello.com/c/yHDCuwF9
4.12 | Sprint 4 | UpdateProfile and UpdateLicense endpoints | Feature |  | 2026-10-31 | 2026-11-02 |  | To do | https://trello.com/c/yY7HQGmO
5.1 | Sprint 5 | ListCustomers controller | Feature |  | 2026-11-03 | 2026-11-05 |  | To do | https://trello.com/c/lI3MsePw
5.2 | Sprint 5 | ListCustomer DTO and its mapper | Feature |  | 2026-11-03 | 2026-11-05 |  | To do | https://trello.com/c/TDfcLpj3
5.3 | Sprint 5 | VerifyLicense endpoint (staff) | Feature |  | 2026-11-05 | 2026-11-06 |  | To do | https://trello.com/c/Gba8Blg4
5.4 | Sprint 5 | ListCars controller | Feature |  | 2026-11-05 | 2026-11-07 |  | To do | https://trello.com/c/LGP4xh0T
5.5 | Sprint 5 | AdminListAllRentals controller | Feature |  | 2026-11-07 | 2026-11-09 |  | To do | https://trello.com/c/0HQMY2zr
5.6 | Sprint 5 | ListPayments controller | Feature |  | 2026-11-09 | 2026-11-11 |  | To do | https://trello.com/c/EQs9Ose5
5.7 | Sprint 5 | ListPayments DTO and its mapper | Feature |  | 2026-11-09 | 2026-11-11 |  | To do | https://trello.com/c/A1ebSNFP
5.8 | Sprint 5 | Testing with the front end | Integrating with Frontend |  | 2026-11-03 | 2026-11-12 |  | To do | https://trello.com/c/3NdSl3Az
5.9 | Sprint 5 | Bug fixing and edits | Testing |  | 2026-11-03 | 2026-11-12 |  | To do | https://trello.com/c/EkeVUfMH
6.1 | Sprint 6 | ApproveRental controller | Feature |  | 2026-11-13 | 2026-11-15 |  | To do | https://trello.com/c/fhxihmyz
6.2 | Sprint 6 | HandOverKeys controller | Feature |  | 2026-11-15 | 2026-11-17 |  | To do | https://trello.com/c/lw0foecX
6.3 | Sprint 6 | Rental rejection controller | Feature |  | 2026-11-17 | 2026-11-19 |  | To do | https://trello.com/c/CNo7iQOy
6.4 | Sprint 6 | AddCar controller | Feature |  | 2026-11-19 | 2026-11-21 |  | To do | https://trello.com/c/JUUM49D7
6.5 | Sprint 6 | AddCar DTO and its mapper | Feature |  | 2026-11-19 | 2026-11-21 |  | To do | https://trello.com/c/YIya8MUK
6.6 | Sprint 6 | Testing with the front end | Integrating with Frontend |  | 2026-11-13 | 2026-11-22 |  | To do | https://trello.com/c/01CM7B17
6.7 | Sprint 6 | Bug fixing and edits | Testing |  | 2026-11-13 | 2026-11-22 |  | To do | https://trello.com/c/mZVKaGMl
7.1 | Sprint 7 | EditCar controller | Feature |  | 2026-11-23 | 2026-11-25 |  | To do | https://trello.com/c/Vwhs7g9J
7.2 | Sprint 7 | RecordReturn controller | Feature |  | 2026-11-23 | 2026-11-25 |  | To do | https://trello.com/c/kvaM6AD2
7.3 | Sprint 7 | Admin profile endpoints | Feature |  | 2026-11-25 | 2026-11-27 |  | To do | https://trello.com/c/mD7RNnDy
7.4 | Sprint 7 | DeleteCar controller | Milestone, Feature |  | 2026-11-25 | 2026-11-29 |  | To do | https://trello.com/c/ErdjjFYd
7.5 | Sprint 7 | Testing with the front end | Integrating with Frontend |  | 2026-11-23 | 2026-12-02 |  | To do | https://trello.com/c/o2jdTlZt
7.6 | Sprint 7 | Bug fixing and edits | Testing |  | 2026-11-23 | 2026-12-02 |  | To do | https://trello.com/c/9UE8HTBT
8.1 | Sprint 8 | Test the whole system and fix any bugs | Testing, Integrating with Frontend |  | 2026-12-02 | 2026-12-25 |  | To do | https://trello.com/c/nw3eoCRm

## Sprints
Wayfare: sprints
Each sprint is one list on the Trello board. Start, End, Cards and Done are formulas over the Sprint backlog sheet.
Sprint | Focus | Trello list | Start | End | Days | Cards | Done | Done %
Sprint 1 | Front-end wireframe and project structure | Sprint 1 - Frontend WireFrame && Project Structure
Sprint 2 | Back-end data and database | Sprint 2 - Backend Data && Database
Sprint 3 | Authentication endpoints and one customer endpoint | Sprint 3 - Authentication Endpoints + one cutomer endpoint
Sprint 4 | Customer endpoints | Sprint 4 - 3 Customer Endpoints
Sprint 5 | Admin listing functionalities | Sprint 5 - Admin Listing Functionalities
Sprint 6 | Admin core functionalities | Sprint 6 - Admin Core Functionalities
Sprint 7 | Admin endpoints, part 2 | Sprint 7 - admin endpoints part 2
Sprint 8 | Final testing | Sprint 8 - Final Testing
Total

## Milestones
Wayfare: milestones
Milestones are the cards with the Milestone label on the Trello board. "End" is the last due date on the board.
Ref | Date | Milestone | Done when | Sprint | Trello card
M1 | 2026-10-11 | DbContext and database ready | The DbContext is set up and the database is created from the models. | Sprint 2 | https://trello.com/c/EZ9lnIYX
M2 | 2026-10-19 | Authentication and authorization live | Login and register run on ASP.NET Core Identity with JWT tokens and roles. | Sprint 3 | https://trello.com/c/YnKxkEPO
M3 | 2026-11-29 | Last app feature built | DeleteCar, the last feature card on the board, is done. | Sprint 7 | https://trello.com/c/ErdjjFYd
End | 2026-12-25 | Final testing complete | The whole system is tested with the front end and the bugs found are fixed. | Sprint 8 | https://trello.com/c/nw3eoCRm

## Package plan
Wayfare: back-end package plan
Snapshot of 16 Oct 2026: card sizes S 2, M 4, L 8 hours, 2 hours a day for each member, every calendar day counts. A package starts when the cards it needs are finished. Start and End come from the Backend Board; Cards, Work, Days and Spare are formulas.
Package | Name | Cards | Work (h) | Start | End | Days | Needs first | Room (days) | Critical path | Trello deadline | Spare (days)
A | Foundation and sign in |  |  | 2026-10-16 | 2026-10-26 |  | Nothing | 0 | Yes | 2026-10-22
B | Accounts and profiles |  |  | 2026-10-16 | 2026-10-29 |  | A (ready 23 Oct) | 4 | No | 2026-11-27
C | Browse cars and request one |  |  | 2026-10-16 | 2026-10-31 |  | A (ready 23 Oct) | 4 | No | 2026-11-02
D | Rental lifecycle |  |  | 2026-10-24 | 2026-11-04 |  | A (ready 23 Oct) and C (ready 17 Oct) | 0 | Yes | 2026-11-25
E | Staff fleet |  |  | 2026-10-23 | 2026-11-04 |  | A (ready 22 Oct) and B (ready 17 Oct) | 0 | Yes | 2026-12-02
F | Staff customers, payments and final test |  |  | 2026-10-24 | 2026-11-08 |  | A (ready 23 Oct) and C (ready 17 Oct) | 0 | Yes | 2026-12-25
Total
Critical path
Step | Package | Cards | From | To
1 | Foundation and sign in | F1 > F2 > F3 > F5 > F6 | 2026-10-16 | 2026-10-23
2 | Rental lifecycle | R2 > R3 > R4 > A1 > A2 > A4 > A3 > A5 > Q5 | 2026-10-24 | 2026-11-04
3 | Staff customers, payments and final test | Q7 | 2026-11-05 | 2026-11-08
If a package on this chain slips a day, the whole back end finishes a day later.

## Package cards
Wayfare: back-end cards in build order
One row per open back-end card, grouped by package. Days = End - Start + 1. Spare = Trello due date - End (negative means the plan ends after the Trello date).
Package | Card | Title | Size | Hours | Start | End | Days | Needs first | Room (days) | Critical | Trello due | Spare (days)
A | F1 | Fix enum typos and add the missing fields | S | 2 | 2026-10-16 | 2026-10-16 |  | Nothing | 0 | Yes | 2026-10-16
A | F2 | Program.cs setup | M | 4 | 2026-10-17 | 2026-10-18 |  | Nothing | 0 | Yes | 2026-10-16
A | F3 | Seed roles, admin account and sample cars | M | 4 | 2026-10-19 | 2026-10-20 |  | F1 (A) | 0 | Yes | 2026-10-17
A | F5 | Authentication and authorization with Identity and JWT | M | 4 | 2026-10-21 | 2026-10-22 |  | F2 (A) | 0 | Yes | 2026-10-19
A | F6 | Login controller, DTO and mapper | S | 2 | 2026-10-23 | 2026-10-23 |  | F5 (A), F3 (A) | 0 | Yes | 2026-10-15
A | Q1 | Create the .http file and the login requests | S | 2 | 2026-10-24 | 2026-10-24 |  | F6 (A) | 9 | No | 2026-10-22
A | Q2 | Sprint 3 test with the front end: sign in and cars | M | 4 | 2026-10-25 | 2026-10-26 |  | F6 (A), F7 (B), C1 (C) | 9 | No | 2026-10-22
B | F4 | Image storage service | M | 4 | 2026-10-16 | 2026-10-17 |  | Nothing | 9 | No | 2026-10-17
B | F7 | Register controller, DTO and mapper | M | 4 | 2026-10-23 | 2026-10-24 |  | F4 (B), F5 (A), F1 (A) | 4 | No | 2026-10-15
B | F8 | ChangePassword endpoint | S | 2 | 2026-10-25 | 2026-10-25 |  | F5 (A) | 4 | No | 2026-10-20
B | P1 | GetUserProfile controller and UserProfileDto | S | 2 | 2026-10-26 | 2026-10-26 |  | F6 (A), F3 (A) | 4 | No | 2026-10-31
B | P2 | UpdateProfile and UpdateLicense endpoints | M | 4 | 2026-10-27 | 2026-10-28 |  | F6 (A), F4 (B), F1 (A) | 4 | No | 2026-11-02
B | P5 | Admin profile endpoints | S | 2 | 2026-10-29 | 2026-10-29 |  | F6 (A), F3 (A) | 4 | No | 2026-11-27
C | M1 | RentalRules service: price, overlap and refund | M | 4 | 2026-10-16 | 2026-10-17 |  | Nothing | 8 | No | 2026-10-17
C | F9 | Branches endpoint | S | 2 | 2026-10-19 | 2026-10-19 |  | F2 (A) | 7 | No | 2026-10-17
C | C1 | ListCar controller, DTO and mapper | M | 4 | 2026-10-23 | 2026-10-24 |  | F3 (A), M1 (C), F5 (A) | 4 | No | 2026-10-17
C | C2 | Car details endpoint | S | 2 | 2026-10-25 | 2026-10-25 |  | C1 (C) | 4 | No | 2026-10-25
C | R1 | RentalRequest controller, DTO and mapper | L | 8 | 2026-10-26 | 2026-10-29 |  | M1 (C), F6 (A), F3 (A) | 4 | No | 2026-10-27
C | Q3 | Sprint 4 test with the front end: requests, cancel and profile | M | 4 | 2026-10-30 | 2026-10-31 |  | R1 (C), R2 (D), R3 (D), R4 (D), P1 (B), P2 (B) | 4 | No | 2026-11-02
D | R2 | ListMyRentals controller, DTO and mapper | M | 4 | 2026-10-24 | 2026-10-25 |  | F6 (A), F3 (A) | 0 | Yes | 2026-10-25
D | R3 | CancelRental controller | S | 2 | 2026-10-26 | 2026-10-26 |  | F6 (A), F3 (A), M1 (C) | 0 | Yes | 2026-10-29
D | R4 | RefuseRental controller (10% fee) | S | 2 | 2026-10-27 | 2026-10-27 |  | F6 (A), F3 (A), M1 (C) | 0 | Yes | 2026-10-31
D | A1 | AdminListAllRentals controller and DTO | M | 4 | 2026-10-28 | 2026-10-29 |  | F6 (A), F3 (A) | 0 | Yes | 2026-11-09
D | A2 | ApproveRental controller | S | 2 | 2026-10-30 | 2026-10-30 |  | F6 (A), F3 (A), M1 (C) | 0 | Yes | 2026-11-15
D | A4 | HandOverKeys controller | S | 2 | 2026-10-31 | 2026-10-31 |  | F6 (A), F3 (A) | 0 | Yes | 2026-11-17
D | A3 | Rental rejection controller | S | 2 | 2026-11-01 | 2026-11-01 |  | F6 (A), F3 (A), M1 (C) | 0 | Yes | 2026-11-19
D | A5 | RecordReturn controller | S | 2 | 2026-11-02 | 2026-11-02 |  | F6 (A), F3 (A), F1 (A) | 0 | Yes | 2026-11-25
D | Q5 | Sprint 6 test with the front end: the staff workflow | M | 4 | 2026-11-03 | 2026-11-04 |  | A2 (D), A3 (D), A4 (D), C4 (E) | 0 | Yes | 2026-11-22
E | C3 | Staff ListCars controller | S | 2 | 2026-10-23 | 2026-10-23 |  | F5 (A), F3 (A) | 3 | No | 2026-11-07
E | C4 | AddCar controller, DTO and mapper | L | 8 | 2026-10-24 | 2026-10-27 |  | F4 (B), F5 (A), F3 (A) | 3 | No | 2026-11-21
E | C6 | DeleteCar controller | S | 2 | 2026-10-28 | 2026-10-28 |  | F5 (A), F3 (A) | 3 | No | 2026-11-29
E | C5 | EditCar controller | M | 4 | 2026-10-29 | 2026-10-30 |  | C4 (E) | 3 | No | 2026-11-25
E | Q6 | Sprint 7 test with the front end: edit, delete, return | M | 4 | 2026-11-03 | 2026-11-04 |  | C5 (E), C6 (E), A5 (D), P5 (B) | 0 | Yes | 2026-12-02
F | P3 | ListCustomers controller and DTO | M | 4 | 2026-10-24 | 2026-10-25 |  | F6 (A), F3 (A) | 5 | No | 2026-11-05
F | P4 | VerifyLicense endpoint (staff) | S | 2 | 2026-10-26 | 2026-10-26 |  | F6 (A), F3 (A), F1 (A) | 5 | No | 2026-11-06
F | M2 | ListPayments controller, DTO and mapper | M | 4 | 2026-10-27 | 2026-10-28 |  | F6 (A), F3 (A), M1 (C) | 5 | No | 2026-11-11
F | Q4 | Sprint 5 test with the front end: staff lists | M | 4 | 2026-10-30 | 2026-10-31 |  | P3 (F), C3 (E), A1 (D), M2 (F) | 4 | No | 2026-11-12
F | Q7 | Final test of the whole system and bug fixing | L | 8 | 2026-11-05 | 2026-11-08 |  | Q2 (A), Q3 (C), Q4 (F), Q5 (D), Q6 (E) | 0 | Yes | 2026-12-25

## Risk register
Wayfare: risk register
Edit only the shaded Likelihood and Impact cells (1 = low, 3 = high). Rating = Likelihood x Impact; 6 or more is High, 3 to 4 is Medium, below 3 is Low. The team leader reviews this sheet every week.
ID | Risk | Cause | Likelihood | Impact | Rating | Level | Prevention and fallback
R1 | A team member drops out or is away | 7 people, exams, other courses | 2 | 3 |  |  | Whole-team cards carry every name, and notes and code stay in shared places, so another member can pick up any card.
R2 | Scope creep | New features keep arriving | 3 | 2 |  |  | The scope is the endpoint list agreed in Sprint 2. New ideas wait for a later sprint and need a change request.
R3 | Front end and back end do not match | Different field names or formats | 3 | 2 |  |  | The endpoint list was written in Sprint 2, DTOs keep the front end's field names, and Sprints 3 to 7 each have a Testing with Frontend card.
R4 | Double booking bug | Two customers get the same car | 2 | 3 |  |  | Overlaps are checked in the back end when a rental request is saved (Sprint 4), not only on screen, and retested in Sprint 8.
R5 | Schedule slips | Late cards push testing out | 3 | 3 |  |  | Card due dates are checked every week. Sprint 8 gives 24 days for final testing and fixes. Low-value features are cut first.
R6 | Poor communication | Messages missed in a big group | 2 | 2 |  |  | One group chat for quick talk, one Teams channel for decisions. Decisions are written in the notes, not only said.
R7 | Lost code or data | Bad merge, deleted files | 1 | 3 |  |  | All code lives in the team GitHub repository set up in Sprint 1, with reviewed merges to main. Weekly database backup.
R8 | Security weakness | Passwords and license data | 2 | 3 |  |  | ASP.NET Core Identity and JWT in Sprint 3, role checks on every admin endpoint, input validation, retested in Sprint 8.
R9 | Bugs found too late | Testing left to the end | 2 | 2 |  |  | Every sprint from Sprint 2 has its own bug-fixing card, and testing with the front end starts in Sprint 3.
R10 | Works on one laptop only | Different setups | 2 | 1 |  |  | The web stack, project structure and NuGet packages were agreed in Sprints 1 and 2. Setup steps go in the README.

## Team
Wayfare: team
Seven members. Names on each Trello card show who works on it.
# | Name | Role
1 | Abdelrahman Hany | Team leader
2 | Kerollos Romany | Team member
3 | Mina Maher | Team member
4 | Samuel Mokhles | Team member
5 | Matthew Ashraf | Team member
6 | Marwan Mohamed | Team member
7 | Basem Hany | Team member